## Test Case
Module Name | Login
Test Case ID | TC_001
Tester Name | Zhaira Nicole A. Pacheco
Test Case Description | To check login functionality of Rogationist College Student Portal
Pre-requisites | 1. Internet Connection 2. Browser (Chrome, Firefox, Edge) 3. Running Rogationist College Student Portal
Environment Information | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop
Test ID | Test Scenario | Test Data | Test Steps | Expected Results | Actual Results | Status | Comments
1 | Check that with the correct username and password able to log in. | Username: CT02032024 Password: ROCS1234! | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Enter the username in username field 4. Enter the password in password field 5. Click on the Login button | Login successful | Login successful | Passed | None
2 | Check that with the correct username and password able to log in. | Username: CT02032024 Password: <invalidpsw> | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Enter the username in username field 4. Enter the password in password field 5. Click on the Login button | an error “Invalid Login Credentials” | "Invalid Login Credentials Please wait 5 seconds to sign in again." | Passed | None
3 | Check that with the correct username and password able to log in. | Username: <invalidun> Password: ROCS1234! | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Enter the username in username field 4. Enter the password in password field 5. Click on the Login button | an error “Invalid Login Credentials” | "Invalid Login Credentials Please wait 5 seconds to sign in again." | Passed | None
4 | Check that with the correct username and password able to log in. | Username: <invalidun> Password: <invalidpsw> | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Enter the username in username field 4. Enter the password in password field 5. Click on the Login button | an error “Invalid Login Credentials” | "Invalid Login Credentials Please wait 5 seconds to sign in again." | Passed | None
Module Name | Login
Test Case ID | TC_002
Tester Name | Zhaira Nicole A. Pacheco
Test Case Description | To check user interface of Rogationist College Student Portal
Pre-requisites | 1. Internet Connection 2. Browser (Chrome, Firefox, Edge) 3. Running Rogationist College Student Portal
Environment Information | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop
Test ID | Test Scenario | Test Data | Test Steps | Expected Results | Actual Results | Status | Comments
1 | Check that the Student Portal should display RC logo | RC Logo | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Locate the RC Logo | RC Logo is displayed in the interface | RC Logo is displayed in the upper left corner | Passed | None
2 | Check that the “RC Student’s Portal” label is present | RC Student’s Portal | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Locate the “RC Student’s Portal” label | “RC Student’s Portal” label is displayed in the interface | “RC Student’s Portal” label is displayed in the center | Passed | None
3 | Check that the “Please sign in with your account..” label exists | “Please sign in with your account..” | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Locate the “Please sign in with your account..” label | “Please sign in with your account..” label is displayed in the interface | “Please sign in with your account..” label is displayed in the center | Passed | None
Module Name | Login
Test Case ID | TC_003
Tester Name | Zhaira Nicole A. Pacheco
Test Case Description | To check validation in the input field of Rogationist College Student Portal
Pre-requisites | 1. Internet Connection 2. Browser (Chrome, Firefox, Edge) 3. Running Rogationist College Student Portal
Environment Information | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop
Test ID | Test Scenario | Test Data | Test Steps | Expected Results | Actual Results | Status | Comments
1 | Check that username field accept only alphanumeric characters | Username: CT02032024 | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Go to create account page 4.Input Correct Data 5. Click on the Submit button | Accout Created | Accout Created | Passed | None
2 | Check that username field accept only alphanumeric characters | Username: <CT0203\^o^/> | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Go to create account page 4.Input Correct Data except Username 5. Click on the Submit button | Invalid Username Format | Username Created | Failed | No indication that the username is invalid
3 | Check that the password field accept any characters | Password: ROCS1234! | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Go to create account page 4.Input Correct Data 5. Click on the Submit button | Accout Created | Accout Created | Passed | Accepts any characters
Module Name | Login
Test Case ID | TC_004
Tester Name | Zhaira Nicole A. Pacheco
Test Case Description | To check the encryption and enabling of form field of Rogationist College Student Portal
Pre-requisites | 1. Internet Connection 2. Browser (Chrome, Firefox, Edge) 3. Running Rogationist College Student Portal
Environment Information | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop
Test ID | Test Scenario | Test Data | Test Steps | Expected Results | Actual Results | Status | Comments
1 | Verify that the Password entered should be encrypted | Password: ••••••••• | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Type in the Password Field | Password: ••••••••• | Password: ••••••••• | Passed | None
2 | Verify Login button should be enabled | Login Button | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Locate the Login Button, Hover to it | Login Button should be enabled | Login Button should be enabled | Passed | None
Module Name | Login
Test Case ID | TC_005
Tester Name | Zhaira Nicole A. Pacheco
Test Case Description | To check if you will be redirected to Facility page of Rogationist College Student Portal
Pre-requisites | 1. Internet Connection 2. Browser (Chrome, Firefox, Edge) 3. Running Rogationist College Student Portal
Environment Information | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop
Test ID | Test Scenario | Test Data | Test Steps | Expected Results | Actual Results | Status | Comments
1 | Inspect the forgot password, user should be redirected to Recover Password Facility page | Recover Password Facility page | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Click the Forgot Password? | Redirected to Recover Password Facility page | Redirected to Recover Password Facility page | Passed | None
2 | Inspect the No Account? Create One., user should be redirected to Member's Registration Facility page | Member's Registration Facility page | 1. Open the browser 2. Launch Rogationist College Student Portal 3. Click the No Account? Create One. | Redirected to Member's Registration Facility page | Redirected to Member's Registration Facility page | Passed | None

## Test Report
Project Status Report
Project Name | Test Login
Project Description | This is a testing project
Project Planned Start Date | 02/24/2024 | Project Actual Start Date | 02/24/2024
Project Planned End Date | 03/25/2024 | Project Actual End Date
Overall Summary
Total # of Test Case | 14
Not Started | 0
In Progress | 0
Passed | 13
Failed | 1
Blocked | 0
Total # of Defects | 1
New | 1
Open | 0
In Progress | 0
Closed | 0
Detailed Report
Test Case ID | Description | Status | Bug ID | Comments
TC_001 | To check login functionality of Rogationist College Student Portal | Passed | Bug_001 | N/A
TC_002 | To check user interface of Rogationist College Student Portal | Passed | Bug_002 | N/A
TC_003 | To check validation in the input field of Rogationist College Student Portal | Passed | Bug_003 | N/A
TC_004 | To check the encryption and enabling of form field of Rogationist College Student Portal | Passed | Bug_004 | N/A
TC_005 | To check if you will be redirected to Facility page of Rogationist College Student Portal | Passed | Bug_005 | N/A

## Test Report 2
Project Status Report
Project Name | Test Project
Project Description | This is a testing project
Project Planned Start Date | 01/20/2024 | Project Actual Start Date | 01/20/2024
Project Planned End Date | 03/25/2024 | Project Actual End Date
Overall Summary
Total # of Test Case | 25
Not Started | 0
In Progress | 0
Passed | 25
Failed | 0
Blocked | 0
Total # of Defects | 10
New | 0
Open | 0
In Progress | 0
Closed | 10
Detailed Report
Test Case ID | Description | Status | Bug ID | Comments
TC_001 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_001
TC_002 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_002
TC_003 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_003
TC_004 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_004
TC_005 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_005
TC_006 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_006
TC_007 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_007
TC_008 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_008
TC_009 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_009
TC_010 | Lorem ipsum dolor sit amet, consectetur | Passed | Bug_010
TC_011 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_012 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_013 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_014 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_015 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_016 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_017 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_018 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_019 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_020 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_021 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_022 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_023 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_024 | Lorem ipsum dolor sit amet, consectetur | Passed
TC_025 | Lorem ipsum dolor sit amet, consectetur | Passed